## Sheet1 (2)
MILESTONE E-MOVEMENT
Modul | Sub Modul/ Function | Target | Percentage
Dashboard | Overall Summary |  | 100%
| Pending application Page |  | 100%
100%
Registeration | Register Online |  | 100%
| Notifification Email to User |  | 0%
| Notifification Email to Admin |  | 100%
| User Profile Change |  | 100%
| Change Password |  | 100%
80%
Timetable | Add Application |  | 100%
| Notify Application to KPP via email if Pegawai | 2014-03-28 | 100%
| Notify Application to Timbalan via email if KPP | 2014-03-28 | 100%
| Notify Appliation to Pengarah via email if Timbalan | 2014-03-28 | 100%
| Pending application Page |  | 100%
| Rejected Application Page |  | 100%
| Notify Reject to User via email | 2014-03-28 | 100%
| Approved application Page |  | 100%
| Select Timetable according to - Pengarah- Semua Sector, Timbalan, KPP, Pegawai Timbalan- Semua KPP & Pegawai dari Sector Yang Sama KPP- Semua Pegawai dari Sector yang sama | 2014-03-27 | 100%
| Notify Approved to User via email | 2014-03-28 | 100%
100%
Calendering | View Calendar Monthly for Pegawai |  | 100%
| View Calendar Monthly for KPP | 2014-03-27 | 100%
| View Calendar Monthly for Timbalan |  | 100%
| View Calendar Monthly for Pengarah |  | 100%
| View Monthly Calendar like Google | 2014-03-29 | 100%
| Click to see detail | 2014-03-29 | 100%
100%
User Permission | Pegawai - add, view |  | 100%
| Ketua Penolong Pengarah- add,view | 2014-03-27 | 100%
| Timbalan - add, view |  | 100%
| Pengarah - view, delete |  | 100%
100%
Admin | Setting Orga |  | 100%
| Setting Function & Sector |  | 100%
| Setting System |  | 100%
100%
Documentation | System Process & Work Flow | 29~31 | 100%
| User Manual | 1~4 | 0%
50%
| Overall Percentage |  | 90%

## Sheet1
MILESTONE E-MOVEMENT
Modul | Sub Modul/ Function
Dashboard | Overall Summary
Pending application Page
Registeration | Register Online
Notifification Email to User
Notifification Email to Admin
User Profile Change
Change Password
Timetable | Add Application
Notify Application to KPP via email if Pegawai
Notify Application to Timbalan via email if KPP
Notify Appliation to Pengarah via email if Timbalan
Pending application Page
Rejected Application Page
Notify Reject to User via email
Approved application Page
Select Timetable according to - Pengarah- Semua Sector, Timbalan, KPP, Pegawai Timbalan- Semua KPP & Pegawai dari Sector Yang Sama KPP- Semua Pegawai dari Sector yang sama
Notify Approved to User via email
Calendering | View Calendar Monthly for Pegawai
View Calendar Monthly for KPP
View Calendar Monthly for Timbalan
View Calendar Monthly for Pengarah
View Monthly Calendar like Google
Click to see detail
User Permission | Pegawai - add, view
Ketua Penolong Pengarah- add,view
Timbalan - add, view
Pengarah - view, delete
Admin | Setting Orga
Setting Function & Sector
Setting System
Documentation | System Process & Work Flow
User Manual